## Summary
Student(s) |  | João Carvalho ¦ Miguel Rossi Seabra |  |  | Class | 3MIEIC2
Program |  | Program 2 - Linear regression |  |  | Programming Language | Java
Instructor |  | ACP |  |  | Start Date
End Date
Parameter |  | Estimated Value | Actual Value
Added and Modified Size (LOC) |  | 208.64 | 0
Time (minutes) |  | 250.368 | 61.5167
Productivity (LOC/Hour) |  | 50
Phase |  | Time in Phase (min.) | Defects Injected | Defects Removed
PLAN | - Planning | 22.6 | 0 | 0
DLD | - Detailed Design | 14.8667 | 0 | 0
CODE | - Code | 24.05 | 0 | 0
UT | - Unit test | 0 | 0 | 0
PM | - Postmortem | 0 | 0 | 0
Total |  | 61.5167 | 0 | 0

## TimeLog
Phase | Start Date and Time (double click to fill) | Interrup. Time (minutes) | Stop Date and Time (double click to fill) | Delta Time (minutes) | Comments
PLAN | 2011-09-30 10:26 |  | 2011-09-30 10:48 | 22.6
DLD | 2011-09-30 10:48 |  | 2011-09-30 11:03 | 14.8667
CODE | 2011-09-30 11:03 | 4 | 2011-09-30 11:31 | 24.05

## DefectLog
Number | Date (double click to fill) | Type | Phase Injected | Phase Removed | Fix Time (min.) | Description

## SizeEstimatingTemplate
New Parts | [5 empty] | Base/Reused Parts
Part name (class or part of class) | Part type | Num. Items (methods) | Items' relative size | Estimated part size (LOC) | Actual size (LOC) | Part name (class / file) | Initial size (LOC) | Estimated added and modified size (LOC) | Actual added and modified size (LOC) | Final size (LOC)
TStudentDistribution | [5 empty] | Function.java | 4 | 0 | 0 | 4
Constructor | Data | 1 | XS | 2.6 |  | GammaFunction.java | 13 | 0 | 0 | 13
CalcProbabilityDensity | Calc | 1 | L | 24.66 |  | NewtonRapsonMethod.java | 13 | 0 | 0 | 13
CacPGivenX, CalcXGivenP | Calc | 2 | M | 22.5 |  | SimpsonMethod.java | 34 | 0 | 0 | 34
LinearRegression
Constructor | Data | 1 | S | 4.79
CalcB0 | Calc | 1 | M | 11.25
CalcB1 | Calc | 1 | M | 11.25
CalcR | Calc | 1 | L | 24.66
Calcyk | Calc | 1 | XS | 2.34
Significance | Calc | 1 | XL | 54.04
Main
GetData | IO | 1 | L | 21.62
PrintData | IO | 1 | XL | 28.93
Total |  |  |  | 208.64 | 0 | Total |  | 0 | 0 | 64
Note on F2: Suggestion: Enter just the total per file

## RelativeSizeTable
Part type (class type) | Description | Item size (method size)
|  | XS | S | M | L | XL
Calc | Calculation object (maths, etc.) | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | Data object (data storage and access) | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
IO | IO object (user interface, file access) | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | Logic object (algorithms, etc.) | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | Set-up object | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | Text object (string/text processing) | 3.75 | 8 | 17.07 | 36.41 | 77.66